## Slide 1
Building a Cloud Center of Excellence
From Scratch — Azure, AWS & Bare Metal
Vince Maidens · August 2026

## Slide 2
Core Principles
• Enable, don't block — self-service by default, guardrails not gates
• Measure everything — FinOps, security posture, adoption velocity
• Start small, scale fast — pilot, prove, then expand
• Hybrid-aware — bare metal is first-class, not legacy
Vince Maidens · August 2026
2/11

## Slide 3
Team Structure (~5-6 FTEs)
Role | Count | Focus
CCoE Leads | 2 | Strategy, executive reporting (Vince Maidens, Peter Main)
Cloud Architect | 1-2 | Azure/AWS standards, design reviews
FinOps Analyst | 1 | Cost visibility, optimisation
Security Lead | 1 | NCSC CSP, IAM, policy
Platform Engineer | 1-2 | Landing zones, IaC, automation
Developer Advocate | 1 | Training, docs, evangelism
Vince Maidens · August 2026
3/11

## Slide 4
24-Week Roadmap
Phase | Weeks | Focus
0 — Foundation | 1-4 | See everything, win fast
1 — Guardrails | 5-10 | Safe self-service
2 — Enablement | 11-16 | Accelerate adoption
3 — Optimisation | 17-24 | Continuous improvement
Vince Maidens · August 2026
4/11

## Slide 5
Phase 0: Quick Wins (First 30 Days)
• Tag compliance report + auto-tag policy — visibility in 1 day
• Rightsize idle VMs — immediate cost savings in 2 days
• Enable Azure Policy baseline — NCSC CSP aligned in 1 day
• Publish Cloud Playbook — how to deploy a web app
• Set up cost alerts — subscription-level governance
• Bare metal risk register — top 10 highest-risk servers
Vince Maidens · August 2026
5/11

## Slide 6
Phase 1: Guardrails (Weeks 5-10)
Azure Landing Zone
• Management group hierarchy aligned to business units
• Separate subscriptions for cost isolation and blast radius
• Azure Blueprints for repeatable deployment
Security
• PIM + Conditional Access baseline (massive win, zero dev friction)
• Managed Identities replacing service accounts
• NCSC CSP aligned Azure Policy initiatives
Bare Metal Governance
• Asset registry, patch SLAs, decommission process
• Integrate monitoring with central Log Analytics
Vince Maidens · August 2026
6/11

## Slide 7
Phase 2: Enablement (Weeks 11-16)
IaC Standards
• Bicep (Azure), Terraform (AWS), Ansible (bare metal)
• Template library: pre-approved patterns for common workloads
• PR reviews for all infrastructure changes
Self-Service Catalogue
• "Deploy a web app" (App Service + SQL + WAF)
• "Deploy containers" (AKS + ACR + App Gateway)
• "Dev/test environment" (sandbox subscription)
• "Connect on-premises" (ExpressRoute + private endpoints)
Training
• "Cloud 101" workshop — hands-on, free sandbox
• Certification targets: AZ-900 (80% staff), AZ-104 (50%), AZ-305 (architects)
Vince Maidens · August 2026
7/11

## Slide 8
Phase 3: Optimisation (Weeks 17-24)
FinOps
• Cost allocation tags enforced across all subscriptions
• Reserved instances / savings plans (1-year and 3-year)
• Auto-shutdown for dev/test environments
• Cost-per-workload dashboard per business unit
Security Hardening
• Zero Trust architecture
• Defender for Cloud on all subscriptions
• Key Vault migration — eliminate hardcoded secrets
• Automated compliance reporting (NCSC CSP)
Bare Metal Modernisation
• Waves: stabilise → automate → assess → migrate
Vince Maidens · August 2026
8/11

## Slide 9
Key KPIs
Category | Metric | Month 6 | Month 12
Cost | Reserved instance coverage | 40% | 70%
Security | Resources compliant with Policy | 80% | 95%
Security | Privileged access via PIM | 100% | 100%
Adoption | New deployments via IaC | 50% | 90%
Adoption | Staff certified (AZ-900+) | 30% | 80%
Bare Metal | Servers with monitoring | 50% | 100%
Vince Maidens · August 2026
9/11

## Slide 10
Immediate Next Steps (This Week)
✅ Executive sponsorship secured — Ciaran Barr (CIO)
Draft CCoE charter — scope, authority, KPIs, team structure
Run Azure resource graph — produce estate summary
Schedule CCoE kickoff — with all potential team members
Identify bare metal inventory owner — who knows what's on-premises?
Set up cost alerts — Azure Cost Management on all subscriptions
Vince Maidens · August 2026
10/11

## Slide 11
Questions?
vmaidens@capita.com